## Ark1
TEAM |  | MEETINGS
Project manager |  | Kickoff meeting (1 hour)
Front-end developer |  | Team meeting disccusting and planning (1hour)
Designer |  | Kickoff meeting (1hour) discuse eventually changes
Content Developer |  | STANDUP MEETING
Photographer |  | Everyday in the morning (10 min)
MONDAY MEETINGS (30MIN)
Interaction meetings (developers and project manager) How are things going
TEAM MEETING 9/12/2019
Team meeting (how are we doing with the project)
FINAL
Final meeting (project manager, team and company)
|  |  | PLAN |  |  |  |  | DESIGN |  |  |  |  | BUILD |  |  |  |  | LAUNCH
18 NOV- 16 DEC 2019 |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4
|  | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
PLAN | RESOURCES
Project planning | Developers, Designer | Planning project
Site structure | Developers, Designer |  |  |  | Site structure
Contract | Project manager | Contract meeting
DESIGN
Styletile | Desinger | [5 empty] | Styletile
Text content | Content Developer | [7 empty] | Text content
Product photoshoot | Photographer | [9 empty] | Photoshoot
Domain | Designer | [6 empty] | Buying
BUILD | [7 empty] | domain
HTML&CSS building, session cookies | Developer | [10 empty] | HTML & CSS BULDING & Session cookies
Contact form | Developer | [12 empty] | Contact form
Search form | Developer | [12 empty] | Search form
Categories form | Developer | [12 empty] | Categories form
Add text content | Developer | [14 empty] | Add text
Add links to social media | Developer | [14 empty] | content
LAUNCH | [14 empty] | Social media |  | Testing
Testing | Developer | [10 empty] | Team meeting | [5 empty] | Cross platform browser testing
Cross platform browser testing | Developer
Validation | Developer | [19 empty] | launch
Launch | Project manager, Developer
Final meeting | Project Manager | [15 empty] | Final
meeting